Section 7 of 13

Team Composition

Keysight Technologies . Agentic AI for SalesOps RFP Response . The Hackett Group on ZBrain . Response date 2026-05-11

A single accountable team for product and services delivery. Continuity is preserved with the engineers who carried out Keysight's earlier POC engagement, so context does not have to be rebuilt from scratch. Final contracting and named individuals are confirmed at MSA signature.

## 7.1 Delivery team during the ten-week engagement

| Role | Count | Responsibility |
| --- | --- | --- |
| Solution Architect | 1 | Overall design and architecture. Stakeholder alignment with Keysight. Single point of accountability for the delivery. |
| AI / ML Lead | 1 | Classification, extraction, confidence calibration, translation. Owns the Knowledge Bases and the operational rule book mapping. |
| AI / ML Engineer | 1 | Pair-builds the AI / ML capabilities. Builds the regression-test harness against the labelled corpus and runs the 60 / 20 / 20 train, validation, test split. |
| Integration Engineer | 2 | Salesforce, Outlook through Microsoft Graph plus IMAP and SMTP, and the Jitterbit channel Keysight provides to Oracle EBS and DocuNet. ServiceNow-side integration is owned by Keysight's dev team; these roles coordinate with that team. |
| Backend Engineer | 1 | Orchestrator services, HITL portal API, audit trail, Knowledge Base authoring API. |
| Frontend Engineer | 1 | Operator HITL portal, Knowledge Base authoring screens, analytics dashboards. |
| QA and UAT Engineer | 1 | Regression test corpus, performance and stress tests, UAT scripts, disaster-recovery verification. |
| Project Manager | 1 | Phase delivery, releases, change control, governance, weekly update call. Owns the shared backlog. |

Nine people across the ten-week engagement.

## 7.2 Week-by-week resource utilisation

Resource allocation by week. Each cell is full-time-equivalent (FTE) days per week for that role: 5 indicates full-time on the engagement, 0 indicates not on the engagement that week. The Solution Architect, AI / ML Lead, and Project Manager are continuous across the engagement. Build roles ramp into MVP Build (Weeks 5 to 8) and wind down across Testing and Tuning (Weeks 9 to 10). QA and UAT capacity ramps from MVP Build into peak coverage across Testing and Tuning.

| Role | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Solution Architect | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 50 |
| AI / ML Lead | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 50 |
| AI / ML Engineer | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 48 |
| Integration Engineer x 2 | 4 | 6 | 8 | 8 | 10 | 10 | 10 | 10 | 8 | 6 | 80 |
| Backend Engineer | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 43 |
| Frontend Engineer | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 40 |
| QA and UAT Engineer | 1 | 2 | 2 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 35 |
| Project Manager | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 50 |
| Total FTE-days per week | 50 | 50 | 48 | 80 | 43 | 40 | 35 | 50 | 396 |  |  |

Engineering continuity from the prior POC sits inside the AI / ML Lead and AI / ML Engineer rows. The same individuals who carried that work are part of the proposed team.

## 7.3 Hypercare team (Weeks 11 to 14, post go-live)

Hypercare runs for the first three months following production cutover. The hypercare team is a focused subset of the delivery team, retained specifically to absorb the first wave of operational findings, the first weeks of real-mail drift, and the first round of CSR feedback at scale. Hypercare is included in the implementation price; no separate fee applies.

| Role | Coverage during hypercare | Responsibility |
| --- | --- | --- |
| Hypercare Lead (Solution Architect) | 0.5 FTE, Keysight business hours | Single point of contact for Keysight during hypercare. Triages every escalation. Owns the hypercare exit report at the end of Week 14. |
| AI / ML Engineer (on-call) | 0.5 FTE, Keysight business hours, 24x7 on-call for critical incidents | Tunes classifier and extraction schemas against the first real CSR corrections. Runs the weekly drift report. Promotes accepted rule-book updates. |
| Integration Engineer (on-call) | 0.5 FTE, Keysight business hours, 24x7 on-call for critical incidents | First-line response on any Salesforce, Outlook, or Jitterbit integration issue (Jitterbit being the channel Keysight provides to Oracle EBS and DocuNet). Coordinates with Keysight's enterprise-system teams, including the Keysight dev team that owns the ServiceNow side. |
| Project Manager | 0.25 FTE, Keysight business hours | Weekly hypercare update call. Weekly status report to Keysight executive sponsors. Coordinates mailbox-by-mailbox cutover for the remaining mailboxes. |
| Account Manager | 0.1 FTE, named contact | Single point of contact for Keysight business sponsors. Monthly business review during hypercare. Hand-off to the steady-state support model at Week 14. |

## 7.4 Steady-state support model (from Week 15 onward)

After hypercare exit the team transitions to the steady-state support model. Tiered support with defined SLAs, scaled to deployed agent count and Keysight's ongoing operational pattern.

| Tier | Coverage | Responsibility |
| --- | --- | --- |
| Tier 1 (L1) support | Keysight business hours | Monitoring, alert triage, first-line response, run-book execution. |
| Tier 2 (L2) support | Keysight business hours | Knowledge-base updates, integration fixes, minor enhancements, regression-test runs. |
| Tier 3 (L3) support | On-call 24 x 7 for critical incidents | Architecture issues, model changes, major incidents, security patches. |
| Account Manager | Named contact | Single point of contact for Keysight. Monthly business review. Capacity planning. Roadmap input. |

## 7.5 Engineering continuity from the prior POC

The same engineers who carried out Keysight's earlier POC engagement are part of the proposed delivery team. The POC work covered the upstream classification pattern, the operational rule book interpretation, the multi-attachment handling, and the Salesforce integration profile. Carrying those engineers into the MVP build means we do not have to rebuild the institutional context that the POC produced.